## STIP_Plan_Detail_Extract_2012-2
Safety Funding Obligation Summary-FY 12, 13
CN | FY | DIST | LEAD AGY | ROUTE | BMPNT | EMPNT | LENGTH | PROJECT LOCATION | WORK TYPE | FUNDING PROGRAM | NOTATION | FUNDING | PDE | TOTAL FUND AMT | FED AMT | STATE AMT | LOCAL AMT | OBLIG AMT | OBLIG DATE | LETTING TYPE | COMMENTS | PROJECT SCOPE DESCRIPTION
1100850 | 2013 | 1 | GRANT COUNTY | 171040 | 0 | 0 | 0 | FROM 0.35 MILES N OF US 180 TO INTERSECTION W/ BEAR MOUNTAIN ROAD | SAFETY | HIGH RISK RURAL ROADS |  | HRRR | Jessica Hunter | 50000 | 46320 | 3680 | 0 |  |  | Local Let | Grant County is working on their agreement request form, expect to obligate design funding in early 2013, and construction funding in August 2013 | INSTALL REGULATORY AND WARNING SIGNS, DELINEATORS, CHEVRONS, SOLAR POWERED FLASHING BEACONS
2100580 | 2012 | 2 | LEA COUNTY | 25E21B | 0 | 33 | 33 | DELAWARE BASIN ROAD (LEA COUNTY ROUTE 21) FROM JCT. NM128 TO JCT. NM 207 | SAFETY | HIGH RISK RURAL ROADS |  | HRRR | Jessica Hunter | 648000 | 600307 | 47693 | 0 | 0 |  | Local Let | Lea County working on environmental certification, anticipate obligation in August 2013 | Fencing to reduce animal hit Crashes
F100170 | 2013 | 5 | NORTH REGION DESIGN CENTER | NM0173 | 1.999 | 3.5 | 1.501 | NM 173 EAST OF AZTEC | SAFETY | HIGH RISK RURAL ROADS |  | HRRR | Isadora Fanning | 2000000 | 1852800 | 147200 | 0 | 0 |  | DOT Let | Letting 9/20/2013 | SHOULDER WIDENING AND VERTICAL CURVE CORRECTION
High Risk Rural Road Total | [13 empty] | 2698000 | 2499427 | 198573 | 0 | 0
9100011 | 2012 | 0 | DISTRICT 5 |  | 0 | 0 | 0 | STATEWIDE ON-CALL SERVICES | PRELIMINARY ENGINEERING | HIGHWAY SAFETY IMPROVEMENT PROGRAM |  | HSIP |  | 1000000 | 926400 | 73600 | 0 | 1000000 | 2012-07-19 | Professional Services
1100730 | 2012 | 1 | DISTRICT 1 | I00025 | 83 | 175 | 92 | FROM ELEPHANT BUTTE INTERCHANGE TO JUNCTION WITH US 60. | SAFETY | HIGHWAY SAFETY IMPROVEMENT PROGRAM |  | HSIP | Maria Hinojos | 1065849 | 987403 | 78446 | 0 | 987402.09 | 2013-01-13 | Price Agreement | Letting 11/2/2013 | Systemic Upgrade Obsolete End treatments on Existing Guardrail on Interstate Routes
LC00090 | 2012 | 1 | DISTRICT 1 | US0070 | 151 | 160 | 9 | /I-25 INTERCHANGE TO BAYLOR CANYON ROAD | SAFETY | HIGHWAY SAFETY IMPROVEMENT PROGRAM |  | HSIP | Jessica Hunter | 2000000 | 1852800 | 147200 | 0 | 2953488 | 2013-01-15 | DOT Let | Was let on 10/19/12, $2,953,487.65. Two Fatalities and one incapacitating injury in cross median crash on US 70 east of Sonoma Ranch Blvd Interchange on 10-31-12 | EXTEND EXISTING Median GUARDRAIL, INSTALL FOUNDATION AND CABLE BARRIER IN MEDIAN to prevent cross median crashes
LC00110 | 2013 | 1 | DONA ANA COUNTY | FL5610 | 0 | 0 | 0 | AT INTERSECTION OF DONA ANA SCHOOL ROAD | SAFETY | HIGHWAY SAFETY IMPROVEMENT PROGRAM |  | HSIP | Jessica Hunter | 285000 | 264024 | 20976 | 0 | 0 |  | Local Let | Dona Ana County ready to advertise RFP for design as soon as funding is obligated (fed form submitted in November 2012); anticipate obligation for construction funding in August 2013. | REALIGN EXISTING Skewed INTERSECTION into two T-Intersections
2100170 | 2012 | 2 | DISTRICT 2 | US0082 | 92.2 | 94.2 | 2 | WEST OF ARTESIA | SAFETY | HIGHWAY SAFETY IMPROVEMENT PROGRAM |  | HSIP | Louis Matta | 1975000 | 1829640 | 145360 | 0 | 2840000 |  | DOT Let | Letting 12/21/2012 | HORIZONTAL CURVE CORRECTION of Two 90-degree curves to One long S-Curve
2100570 | 2012 | 2 | CURRY COUNTY | US0060 | 384.5 | 385.5 | 1 | US 84 EASTBOUND | SAFETY | HIGHWAY SAFETY IMPROVEMENT PROGRAM |  | HSIP | Jessica Hunter | 250000 | 231600 | 18400 | 0 | 231600 | 2012-04-02 | Local Let | FHWA approved fed form 4/2/12 and Curry County awarded to K Barnett & Sons on 8/10/12. | DECELERATION/ACCELERATION LANE
2101140 | 2013 | 2 | DISTRICT 2 | NM0532 | 6.89 | 11.95 | 5.06 | FROM ALTO (NW OF RUIDOSO) TO LINCOLN/OTERO COUNTY LINE | SAFETY | HIGHWAY SAFETY IMPROVEMENT PROGRAM |  | HSIP | DISTRICT 2 | 1385000 | 1283064 | 101936 | 0 | 0 |  | DOT Let
2101150 | 2013 | 2 | DISTRICT 2 | NM0244 | 0 | 29.4 | 29.4 | CLOUDCROFT TO MESCALERO | SAFETY | HIGHWAY SAFETY IMPROVEMENT PROGRAM |  | HSIP | SHERRI HOLLIEFIELD | 1000000 | 926400 | 73600 | 0 | 0 |  | DOT Let
3100380 | 2012 | 3 | DISTRICT 3 |  | 0 | 0 | 0 | INDIAN RESERATION ROAD (IRR) 84 (SECTION 10), SAN FELIPE PUEBLO AT THE SAN FELIPE HEAD START INTERSECTION | SAFETY | HIGHWAY SAFETY IMPROVEMENT PROGRAM |  | HSIP | Jill Mosher | 263521 | 244126 | 19395 | 0 | 304781 | 2012-07-11 | DOT Let | This project was never submitted to nor reviewed by the Safety Project Engineer in the Traffic Technical Support Bureau as part of the NM HSIP | ADDING TURN LANES, DECELERATION AND ACCELERATION LANES
3100400 | 2012 | 3 | DISTRICT 3 | I00025 | 0 | 0 | 0 | FROM BERNARDO TO LA BAJADA | SAFETY | HIGHWAY SAFETY IMPROVEMENT PROGRAM |  | HSIP | Antonio Jaramillo | 250000 | 231600 | 18400 | 0 | 250000 | 2012-06-15 | DOT Let | Letting scheduled for 05/17/13 | Systemic Upgrade Obsolete End treatments on Existing Guardrail on Interstate Routes
3100450 | 2013 | 3 | TOWN OF PERALTA | 615003 | 0 | 0 | 0 | CHUGHOLE LN FROM HERRON RD TO CHAPARRAL LN, PERALTA | SAFETY | HIGHWAY SAFETY IMPROVEMENT PROGRAM |  | HSIP | LOUIE VALDEZ | 200000 | 185280 | 14720 | 0 | 0 |  | Local Let
A300024 | 2012 | 3 | DISTRICT 3 | I00025 | 213.6 | 220.46 | 6.86 | I-25 MEDIAN FENCE INSTALLATION - FROM BROADWAY BLVD INTERCHANGE VICINITY (MP 213.60) TO RIO BRAVO BLVD INTERCHANGE VICINITY (MP 220.46) | SAFETY | HIGHWAY SAFETY IMPROVEMENT PROGRAM |  | HSIP | Thomas Kratochvil | 600000 | 555840 | 44160 | 0 |  |  | DOT Let | Project construction is complete | INSTALL MEDIAN Field FENCING for Access Control to prevent intentional illegal cross median U-Turn movements by motor vehicles
A300653 | 2012 | 3 | LOS LUNAS | NM0006 | 36 | 36.2 | 0.2 | NM 6 & NM 263 TRAFFIC SAFETY AND CAPACITY ENHANCEMENTS - NM 6 @ NM 263 | SAFETY | HIGHWAY SAFETY IMPROVEMENT PROGRAM |  | HSIP | Ozzie | 280000 | 259392 | 20608 | 0 | 280000 | 2012-07-13 | Local Let | awarded project on 11/18/12 | BUILD NEW EASTBOUND RIGHT-HAND TURN BAY ONTO NM 263. UPGRADE PEDESTRIAN FACILITIES AND RELATED SIGNAL UPGRADES.
A300081 | 2013 | 3 | MRTD (RIO METRO) |  | 0 | 0 | 0 | COMMUTER RAIL: ISLETA PUEBLO QUIET ZONE & RR CROSSING CONSOLIDATION - FROM XING #019452T, 019451L, 019450E, TO 019449K, 019445H, 019443U & 019442M | PRELIMINARY ENGINEERING | HIGHWAY SAFETY IMPROVEMENT PROGRAM |  | HSIP | Ozzie | 100000 | 92640 | 0 | 7360 | 100000 | 2012-07-13 | Local Let | Preliminary Engineering phase of project | PERMANENTLY CLOSE SOME CROSSING TO CONSOLIDATE CROSSINGS, REALIGN ROADWAYS AT OTHER Crossings, install flashers, gates, and other safety devices
A300650 | 2013 | 3 | ALBUQUERQUE | FL5092 | 2.03 | 2.23 | 0.2 | RIO GRANDE BLVD INTERSECTION IMPROVEMENTS - FROM I-40 TO GRIEGOS RD | SAFETY | HIGHWAY SAFETY IMPROVEMENT PROGRAM |  | HSIP | Ozzie | 1000000 | 926400 | 73600 | 0 | local funds/denied funds |  | Local Let | Local groups and decisionmakers in ABQ are still in conflict over whether or not to implement this project. Will obligate in March 2013. | Replace existing signalized intersection at Rio Grande Blvd NW at Candelaria Rd NW with a one lane roundabout. Already HSIP safety funds in the amount of $150,000 for design and $1,500,000 for construction were approved for this project. The revised grand total requested by City of ABQ during FY 2012 for an additional $1,000,000 for $2,650,000 was rejected by NM HSIP. It is unknown for what project phase the additional $1,000,000 was needed
A300652 | 2013 | 3 | BERNALILLO COUNTY | FL5095 | 0.19 | 0.49 | 0.3 | OLD COORS RD & SAGE RD INTERSECTION IMPROVEMENTS - OLD COORS RD @ SAGE RD | SAFETY | HIGHWAY SAFETY IMPROVEMENT PROGRAM |  | HSIP | Ozzie | 480000 | 444672 | 35328 | 0 | 0 |  | Local Let | Original much higher amount funding request for HSIP safety funds of which the bulk of the cost was for a storm drainage facility was rejected, will obligated in February 2013 | REALIGN INTERSECTION TO ELIMINATE SKEW AND IMPROVE SIGHT-DISTANCE AND INSTALL PERMANENT TRAFFIC SIGNALS.
A301090 | 2013 | 3 | DISTRICT 3 |  | 0 | 0 | 0 | NM 47 SAFETY PROJECT - FROM CHICAL RD (MP 35) TO NM 147 (MP 38) | SAFETY | HIGHWAY SAFETY IMPROVEMENT PROGRAM |  | HSIP | Priscilla Benavides | 620000 | 574368 | 45632 | 0 | 771777.85 | 2012-12-18 | DOT Let | Scheduled for let on 01/18/13 | INTERSECTION SAFETY IMPROVEMENTS, including warning signs and pavement markings, upgraded pedestrian crosswalk signals
A301170 | 2013 | 3 | DISTRICT 3 |  | 0 | 0 | 0 | NM 333 & NM 217 INTERSECTION IMPROVEMENTS - FROM MP 15.2 ON NM 333 TO MP 10.5 ON NM 217 | SAFETY | HIGHWAY SAFETY IMPROVEMENT PROGRAM |  | HSIP | Antonio Jaramillo | 750000 | 694800 | 55200 | 0 | 0 |  | DOT Let | Scheduled for let on 03/15/13 | CONSTRUCT LEFT TURN LANES ON NM 333 BOTH EB AND WB & REDEFINE THE INTERSECTION REDUCING ITS WIDTH, ETC. INCLUDES PAVEMENT MARKINGS, SIGNAGE, REDEFINING ACCESS EXISTING INGRESS & EGRESS ACCESS TO SELECTED MAILBOX CLUSTERS & POSSIBLE LIGHTING IMPROVEMENTS.
A301240 | 2013 | 3 | LOS LUNAS |  | 0 | 0 | 0 | NM 47 & APPALOOSA DR INTERSECTION IMPROVEMENTS | SAFETY | HIGHWAY SAFETY IMPROVEMENT PROGRAM |  | HSIP | Ozzie | 85000 | 78744 | 6256 | 0 | 0 |  | Local Let | Will obligate in 02/2013 | CONSTRUCT MEDIAN IMPROVEMENTS; INCLUDES: SIGNAGE, MARKINGS, SIDEWALK IMPROVEMENTS AND ADA COMPLIANCE AND CONSTRUCTION OF TURN-BAY(S).
A301250 | 2013 | 3 | CORRALES |  | 0 | 0 | 0 | CORRALES SAFETY PROJECT - DIGITAL SPEED WARNING SIGNS - VARIOUS ROADS IN CORRALES | SAFETY | HIGHWAY SAFETY IMPROVEMENT PROGRAM |  | HSIP | Ozzie | 103000 | 95419 | 7581 | 0 | 0 |  | Local Let | The village needs to execute the agreement and return to the DOT, will obligate by 01/2013 | CORRALES SAFETY PROJECT - DIGITAL SPEED WARNING SIGNS - VARIOUS ROADS IN CORRALES
4100620 | 2012 | 4 | SAN MIGUEL COUNTY | 47A11A | 2.81 | 3.21 | 0.4 | MONTEZUMA, NEAR UNITED WORLD COLLEGE | PRELIMINARY ENGINEERING | HIGHWAY SAFETY IMPROVEMENT PROGRAM |  | HSIP | SAN MIGUEL COUNTY | 36533 | 33844 | 2689 | 0 | 118999 | 2012-09-21 | Local Let
4100630 | 2012 | 4 | DISTRICT 4 | NM0421 | 8 | 8.2 | 0.2 | @TEXAS S/L | SAFETY | HIGHWAY SAFETY IMPROVEMENT PROGRAM |  | HSIP | MOHAMAD ASSAAD | 300000 | 277920 | 22080 | 0 | 294432 | 2012-07-11 | DOT Let
4100620 | 2012 | 4 | SAN MIGUEL COUNTY | 47A11A | 2.81 | 3.21 | 0.4 | MONTEZUMA, NEAR UNITED WORLD COLLEGE | PRELIMINARY ENGINEERING | HIGHWAY SAFETY IMPROVEMENT PROGRAM |  | HSIP | Margaret | 36533 | 33844 | 2689 | 0 | 118999 | 2012-09-21 | Local Let | Preliminary Engineering phase | INSTALL GUARDRAIL PLUS FILL MATERIAL AND SHOT CRETE
5100110 | 2012 | 5 | DISTRICT 5 | NM0574 | 0 | 0.75 | 0.75 | CITY OF AZTEC, INTERSECTION WITH NM 516 | RIGHT OF WAY | HIGHWAY SAFETY IMPROVEMENT PROGRAM |  | HSIP | MARGARET HAYNES | 2500 | 2316 | 184 | 0 | 2500 | 2012-09-12 | DOT Let
5100110 | 2012 | 5 | DISTRICT 5 | NM0574 | 0 | 0.75 | 0.75 | CITY OF AZTEC, INTERSECTION WITH NM 516 | UTILITIES | HIGHWAY SAFETY IMPROVEMENT PROGRAM |  | HSIP | MARGARET HAYNES | 10000 | 9264 | 736 | 0 | 0 |  | DOT Let
5100110 | 2012 | 5 | DISTRICT 5 | NM0574 | 0 | 0.75 | 0.75 | CITY OF AZTEC, INTERSECTION WITH NM 516 | RIGHT OF WAY | HIGHWAY SAFETY IMPROVEMENT PROGRAM |  | HSIP | MARGARET HAYNES | 17500 | 16212 | 1288 | 0 | -2500 | 2012-09-13 | DOT Let
5100590 | 2012 | 5 | DISTRICT 5 |  | 0 | 0 | 0 | GUTIERREZ STREET @ POJOAQUE PUEBLO | PRELIMINARY ENGINEERING | HIGHWAY SAFETY IMPROVEMENT PROGRAM |  | HSIP | DAVE QUINTANA | 15000 | 13896 | 1104 | 0 | 15000 | 2013-01-25 | DOT Let
5100590 | 2012 | 5 | DISTRICT 5 |  | 0 | 0 | 0 | GUTIERREZ STREET @ POJOAQUE PUEBLO | RECONSTRUCTION- NO ADDED CAPACITY | HIGHWAY SAFETY IMPROVEMENT PROGRAM |  | HSIP | DAVE QUINTANA | 705000 | 653112 | 51888 | 0 | 743928 | 2013-01-25 | DOT Let
G500040 | 2012 | 5 | DISTRICT 4 | NM0068 | 0 | 4.283 | 4.283 | VARIOUS LOCATIONS ALONG US 84/285, NM 68 AND NM 76 WITHIN THE CITY OF ESPANOLA | SAFETY | HIGHWAY SAFETY IMPROVEMENT PROGRAM |  | HSIP |  | 116933 | 108327 | 0 | 8606 | 98410 | 2013-01-15 | DOT Let | Was let on 10/19/12, $96,938.64 | INSTALL SOLAR POWERED DIGITAL SPEED DISPLAYS AND RED FLASHING BEACONS
G500040 | 2012 | 5 | DISTRICT 4 | NM0068 | 0 | 4.283 | 4.283 | VARIOUS LOCATIONS ALONG US 84/285, NM 68 AND NM 76 WITHIN THE CITY OF ESPANOLA | SAFETY | HIGHWAY SAFETY IMPROVEMENT PROGRAM |  | HSIP |  | 116933 | 108327 | 0 | 8606 | 98410 | 2013-01-15 | DOT Let | Was let on 10/19/12, $96,938.64 | INSTALL SOLAR POWERED DIGITAL SPEED DISPLAYS AND RED FLASHING BEACONS
5100080 | 2013 | 5 | DISTRICT 4 | NM0074 | 3.4 | 4.1 | 0.7 | POPAY ROAD, OHKAY OWINGEH PUEBLO | PRELIMINARY ENGINEERING | HIGHWAY SAFETY IMPROVEMENT PROGRAM | FY 2011 HSIP FUNDS MOVED TO FY 2012 | HSIP | Margaret | 1000000 | 926400 | 73600 | 0 |  |  | DOT Let | Scheduled for let on 11/21/14 | INTERSECTION IMPROVEMENTS FOR SIGHT DISTANCE,
5100620 | 2013 | 5 | DISTRICT 5 | NM0502 | 10 | 15 | 5 | POJOAQUE TO LOS ALAMOS | SAFETY | HIGHWAY SAFETY IMPROVEMENT PROGRAM | PROJECT FUNDED WITH HSIP MONIES FOR FY 2011 MOVED INTO FY 2012 | HSIP | Will Alaxander | 17000 | 15749 | 1251 | 0 | 0 |  | DOT Let |  | (Systemic HSIP Safety Improvement) Shoulder RUMBLE STRIPS
5100640 | 2013 | 5 | DISTRICT 5 | NM0068 | 29.2 | 33.5 | 4.3 | VELARDE TO HORSE SHOE CURVE | SAFETY | HIGHWAY SAFETY IMPROVEMENT PROGRAM | FY 2011 MONIES MOVED TO FY 2012 | HSIP | Will Alaxander | 245400 | 227339 | 18061 | 0 | 0 |  | Price Agreement | Letting 8/16/2013 | Shooulder CABLE BARRIER REPLACEMENT OF FUNCTIONALLY OBSOLETE shoulder Guardrail SECTIONS AND UPGRADES OF FUNCTIONALLY OBSOLETE Exisiting Guardrail END TREATMENTS for shielding from roadside fixed object hazards and steep roadside side slopes
5100720 | 2013 | 5 | NORTH REGION DESIGN CENTER | NM0068 | 17.283 | 18.083 | 0.8 | NM 68 VELARDE CANYON CIVIL ENGINEERS LANDMARK, at Begin/End Mpnt 17.283 to 18,083 and second section at Quartzite at Beg/End Mpnt: 28.839 - 29.472 | SAFETY | HIGHWAY SAFETY IMPROVEMENT PROGRAM |  | HSIP |  | 400000 | 370560 | 29440 | 0 | 0 |  | DOT Let | Two separate roadway sections of NM 68 | ROADWAY LIGHTING to reduce night time crashes
6100180 | 2013 | 6 | DISTRICT 6 | I00040 | 124.4 | 125.4 | 1 | NEAR EXIT 126 ON I-40. | SAFETY | HIGHWAY SAFETY IMPROVEMENT PROGRAM |  | HSIP | BRYAN PETERS | 800000 | 741120 | 58880 | 0 | 0 |  | DOT Let
6100770 | 2013 | 6 | DISTRICT 6 | US0550 | 63.3 | 63.3 | 0 | WITH NM 197 | SAFETY | HIGHWAY SAFETY IMPROVEMENT PROGRAM |  | HSIP | DISTRICT 6 | 104000 | 96346 | 7654 | 0 | 0 |  | DOT Let
HISP Funding Total | [13 empty] | 17615702 | 16319188 | 1271942 | 24572 | 11207226.94
RR00010 | 2013 | 0 | TRANSIT / RAIL BUREAU |  | 0 | 0 | 0 | STATEWIDE | RAIL/HIGHWAY CROSSING | RAILROAD CROSSING - PROTECTIVE DEVICES |  | RRP | John Whatley | 917144 | 849642 | 67502 | 0 | 0 |  | Other
3100390 | 2012 | 3 | TRANSIT / RAIL BUREAU | 610269 | 0 | 0 | 0 | NOTRH BELEN | RAIL/HIGHWAY CROSSING | RAILROAD CROSSING - PROTECTIVE DEVICES |  | RRP | John Whatley | 47571 | 44070 | 3501 | 0 | 47571 | 2012-07-17 | Other |  | LIGHTS & GATES
3100410 | 2013 | 3 | TRANSIT / RAIL BUREAU | US0060 | 0 | 0 | 0 | PAIZALAS RD. DOT # 019504 H NORTH OF US 60 AND SOUTH OF BELEN. RAILROAD MP IS 0948.12 AND THE CROSSING IS ABOUT ONE MILE NORTH OF THE 175 EXIT ON I-25 BUT THE CROSSING IS ABOUT ¼ MILE EAST OF NM 116. | SAFETY | RAILROAD CROSSING - PROTECTIVE DEVICES |  | RRP | John Whatley | 385000 | 346500 | 38500 | 0 | 305036 | 2012-12-06 | DOT Let |  | LIGHTS, GATES AND NEW CONCRETE SURFACE
4100690 | 2013 | 4 | TRANSIT / RAIL BUREAU |  | 0 | 0 | 0 | UNION COUNTY RD., MT. DORA, WEESE RD. | RAIL/HIGHWAY CROSSING | RAILROAD CROSSING - PROTECTIVE DEVICES |  | RRP | John Whatley | 70117 | 64956 | 5161 | 0 | 70117 | 2012-12-06 | Other |  | CONCRETE SURFACE & LIGHTS
S100180 | 2013 | 5 | TRANSIT / RAIL BUREAU | FR2101 | 0 | 0 | 0 | SFSRR RAILROAD CROSSING 013826B FR 2101 (RABBIT ROAD) SANTA FE | RAIL/HIGHWAY CROSSING | RAILROAD CROSSING - PROTECTIVE DEVICES |  | RRP | John Whatley | 264000 | 237600 | 26400 | 0 | 0 |  | DOT Let |  | INSTALLATION OF GATES, SURFACING AND 12 INCH LED FLASHERS
6100363 | 2013 | 6 | TRANSIT / RAIL BUREAU | FL5459 | 0 | 0.2 | 0.2 | ALLISON ROAD INTERSECTION WITH NM 118 IN GALLUP NM. | SAFETY | RAILROAD CROSSING - PROTECTIVE DEVICES |  | RRP | John Whatley | 50000 | 45000 | 5000 | 0 | 0 |  | Other
6100364 | 2013 | 6 | TRANSIT / RAIL BUREAU | 31001B | 0 | 0.2 | 0.2 | MENTMORE ROAD OVER BNSF RAILROAD TRACKS IN GALLUP NM. | SAFETY | RAILROAD CROSSING - PROTECTIVE DEVICES |  | RRP | John Whatley | 50000 | 45000 | 5000 | 0 | 0 |  | DOT Let
Rail Road Protective Devices Total | [13 empty] | 19165102 | 17754553 | 1385977 | 24572 | 11207226.94
RR00010 | 2013 | 0 | TRANSIT / RAIL BUREAU |  | 0 | 0 | 0 | STATEWIDE | RAIL/HIGHWAY CROSSING | RAILROAD CROSSING - HAZARD ELIMINATION |  | RRS | John Whatley | 307142 | 284536 | 22606 | 0 | 0 |  | Other
1100390 | 2012 | 1 | TRANSIT / RAIL BUREAU |  | 0 | 0 | 0 | WEST DEMING RD., DEMING (UP) | SAFETY | RAILROAD CROSSING - HAZARD ELIMINATION |  | RRS | Railroad | 300000 | 270000 | 30000 | 0 | 0 |  | Other |  | LIGHTS & GATES
1100740 | 2013 | 1 | DISTRICT 1 | NM0158 | 0 | 0 | 0 | 7 MILES NORTH OF LAS CRUCES LUJAN HILL RD BETWEEN VALLEY DR AND DONA ANA ROAD | RAIL/HIGHWAY CROSSING | RAILROAD CROSSING - HAZARD ELIMINATION |  | RRS | Rail Section | 180000 | 162000 | 18000 | 0 | 60067 | 2012-12-06 | DOT Let |  | INSTALL CONCRETE SURFACE AND LIGHTS AT BNSF RAIL CROSSING 019679L
1100750 | 2012 | 1 | TRANSIT / RAIL BUREAU |  | 0 | 0 | 0 | 0.5 MILES SOUTH OF INTERSECTION OF NM 404 AND NM 478 ON WHISPERING DOVE RD | RAIL/HIGHWAY CROSSING | RAILROAD CROSSING - HAZARD ELIMINATION |  | RRS | Rail Section | 275000 | 254760 | 20240 | 0 | 209840 | 2012-07-17 | DOT Let |  | INSTALLATION OF LIGHTS AND GATES AT BNSF RAILROAD CROSSING 019748S
1100790 | 2013 | 1 | TRANSIT / RAIL BUREAU | 111009 | 0 | 0 | 0 | 2 MILES E OF US 60/I-25 INTERCHANGE, ON E SIDE OF I-25 | RAIL/HIGHWAY CROSSING | RAILROAD CROSSING - HAZARD ELIMINATION |  | RRS | Rail Section | 48000 | 43200 | 4800 | 0 | 0 |  | DOT Let |  | ADD CONCRETE SURFACE AT BNSF CROSSING #019507D
2100970 | 2012 | 2 | TRANSIT / RAIL BUREAU |  | 0 | 0 | 0 | VARIOUS LOCATION THROUGHOUT D2 ALONG RAILROAD | RAIL/HIGHWAY CROSSING | RAILROAD CROSSING - HAZARD ELIMINATION |  | RRS | Rail Section | 120000 | 111168 | 8832 | 0 | 25000 | 2012-07-17 | DOT Let |  | DISTRICT WIDE SWRR SIGNAGE UPGRADE
2100980 | 2013 | 2 | TRANSIT / RAIL BUREAU | NM0267 | 0 | 0 | 0 | SOUTH OF INTERSECTION OF US 60 AND NM 276 (12TH ST). | RAIL/HIGHWAY CROSSING | RAILROAD CROSSING - HAZARD ELIMINATION |  | RRS | Rail Section | 70000 | 63000 | 7000 | 0 | 0 |  | DOT Let |  | MEDIAN AND APPROACH WORK AT BNSF RAILROAD CROSSING 019211E
2100990 | 2013 | 2 | TRANSIT / RAIL BUREAU | FL6308 | 0 | 0 | 0 | EAST OF INTERSECTION OF NM 2 AND 5TH ST AT RAIL CROSSING | RAIL/HIGHWAY CROSSING | RAILROAD CROSSING - HAZARD ELIMINATION |  | RRS | Rail Section | 384000 | 345600 | 38400 | 0 | 175384 | 2012-12-06 | DOT Let |  | ADDITION OF CONCRETE SURFCE WITH ADVANCED WARNING SIGNS AND GATES AT SWRR CROSSING 019956T
2101000 | 2013 | 2 | TRANSIT / RAIL BUREAU | 53084 | 0 | 0 | 0 | INTERSECTION OF COUNTY ROAD 84 AND CHOCTAW RD | RAIL/HIGHWAY CROSSING | RAILROAD CROSSING - HAZARD ELIMINATION |  | RRS | Rail Section | 55000 | 49500 | 5500 | 0 | 25573 | 2012-12-06 | DOT Let |  | ADDITION OF CONCRETE SURFACE AND SIGNAGE AT SWRR CROSSING 019948B
2101010 | 2013 | 2 | TRANSIT / RAIL BUREAU | NM0031 | 0 | 0 | 0 | 0.7 MILES NORTHEAST OF INTERSECTION OF NM 31 AND CR 801 | RAIL/HIGHWAY CROSSING | RAILROAD CROSSING - HAZARD ELIMINATION |  | RRS | Rail Section | 475000 | 427500 | 47500 | 0 | 220563 | 2012-12-06 | DOT Let |  | NEW GATES TO GO WITH EXITING LIGHTS AND CONCRETE SURFACE AT SWRR CROSSING 020243G
2101020 | 2013 | 2 | TRANSIT / RAIL BUREAU | NM0031 | 0 | 0 | 0 | 1.6 MILES NORTH OF INTERSECTION OF NM 31 AND NM 128 | RAIL/HIGHWAY CROSSING | RAILROAD CROSSING - HAZARD ELIMINATION |  | RRS | Rail Section | 446000 | 401400 | 44600 | 0 | 216595 | 2012-12-06 | DOT Let |  | NEW CONCRETE SURFACE & GATES WITH CURRENT LIGHTS AT SWRR CROSSING 020240L
2101030 | 2013 | 2 | TRANSIT / RAIL BUREAU | NM0031 | 0 | 0 | 0 | 4 MILES EAST OF INTERSECTION OF NM 31 AND US 285. | RAIL/HIGHWAY CROSSING | RAILROAD CROSSING - HAZARD ELIMINATION |  | RRS | Rail Section | 450000 | 405000 | 45000 | 0 | 205745 | 2012-12-06 | DOT Let |  | NEW CONCRETE SURFACE, GATES AND 12 LED LIGHTS AT SWRR CROSSING 020230F
2101040 | 2013 | 2 | TRANSIT / RAIL BUREAU | FL4918 | 0 | 0 | 0 | 0.6 MILES E OF INTERSECTION WITH US 82 (RELIEF ROUTE) | RAIL/HIGHWAY CROSSING | RAILROAD CROSSING - HAZARD ELIMINATION |  | RRS | Rail Section | 10000 | 9000 | 1000 | 0 | 0 |  | DOT Let |  | BRING UPRR CROSSING 741937B INTO COMPLIANCE
2101050 | 2013 | 2 | TRANSIT / RAIL BUREAU | NM0031 | 0 | 0 | 0 | INTERSECTION OF NM 31 AND US 285. | RAIL/HIGHWAY CROSSING | RAILROAD CROSSING - HAZARD ELIMINATION |  | RRS | Rail Section | 700000 | 630000 | 70000 | 0 | 0 |  | DOT Let |  | NEW CONCRETE SURFACE AND 3 GATES WITH LIGHTS AT SWRR CROSSING 010141N
RR00011 | 2013 | 3 | TRANSIT / RAIL BUREAU |  | 0 | 0 | 0 | OFF OF NM 314 SOUTH OF LOS LUNAS DOT #019469N | RAIL/HIGHWAY CROSSING | RAILROAD CROSSING - HAZARD ELIMINATION |  | RRS | John Whatley | 72000 | 66701 | 5299 | 0 | 0 |  | Price Agreement
RR00012 | 2013 | 3 | TRANSIT / RAIL BUREAU |  | 0 | 0 | 0 | OFF OF NM 314 SOUTH OF LOS LUNAS DOT #019466P | RAIL/HIGHWAY CROSSING | RAILROAD CROSSING - HAZARD ELIMINATION |  | RRS | John Whatley | 72000 | 66701 | 5299 | 0 | 0 |  | Price Agreement
4100680 | 2013 | 4 | TRANSIT / RAIL BUREAU |  | 0 | 0 | 0 | PARK ST., WAGON MOUND, MORA | RAIL/HIGHWAY CROSSING | RAILROAD CROSSING - HAZARD ELIMINATION |  | RRS | John Whatley | 340000 | 306000 | 34000 | 0 | 0 |  | Other |  | STRAIGHTEN INTERSECTION, CONCRETE SURFACE & MEDIANS
6100360 | 2013 | 6 | TRANSIT / RAIL BUREAU | FL5950 | 0 | 0 | 0 | EL MORRO RD., NEAR GRANTS (BNSF) | SAFETY | RAILROAD CROSSING - HAZARD ELIMINATION |  | RRS |  | 45000 | 41688 | 3312 | 0 | 0
Rail Road Crossing Safety Total | [13 empty] | 4349142 | 3937754 | 411388 | 0 | 1138767
W900060 | 2012 | 0 | NMDOT - Safe Routes to Schools Program |  | 0 | 0 | 0 | SAFE ROUTES TO SCHOOL | FACILITIES FOR PEDESTRIANS & BICYCLES | SAFE ROUTES TO SCHOOL- FLEXIBLE FOR INFR |  | SRSF | Jessica Griffin | 50000 | 50000 | 0 | 0 | 0 |  | Price Agreement | Still unsure if FHWA is going to approve. | BIKE RACKS
W900061 | 2012 | 0 | NMDOT - Safe Routes to Schools Program |  | 0 | 0 | 0 | SAFE ROUTES TO SCHOOL | SAFETY AND EDUCATION FOR PEDESTRIANS/BIC | SAFE ROUTES TO SCHOOL- FLEXIBLE FOR INFR |  | SRSF | Jessica Griffin | 100000 | 100000 | 0 | 0 | 0 |  | Other | Still unsure if FHWA is going to approve. | SAFETY EDUCATION
SRSF Total | [13 empty] | 150000 | 150000 | 0 | 0 | 0
W900030 | 2013 | 0 | NMDOT - Safe Routes to Schools Program |  | 0 | 0 | 0 | SRTS- SALARIES (PLACEHOLDER) | ADMINISTRATION | SAFE ROUTES TO SCHOOL- INFRASTRUCTURE | SALARY FOR FY 2013 | SRSI | Jessica Griffin | 65000 | 65000 | 0 | 0 | 0 |  |  |  | SRTS- SALARIES (PLACEHOLDER)
W100040 | 2012 | 1 | MESILLA |  | 0 | 0 | 0 | VARIOUS LOCAL STREETS AROUND MESILLA VALLEY SCHOOLS | OTHER | SAFE ROUTES TO SCHOOL- INFRASTRUCTURE |  | SRSI | Jessica Griffin | 250000 | 250000 | 0 | 0 | 250000 | 2012-09-18 | Local Let |  | CROSSWALKS, FLASHERS, SIGNAGE & SIDEWALK REPAIRS
W100071 | 2012 | 1 | DEMING |  | 0 | 0 | 0 | VARIOUS LOCAL STREETS IN VICINITY OF RUBEN S. TORRES ELEMENTARY SCHOOL CITY OF DEMING PHASE 2 | FACILITIES FOR PEDESTRIANS & BICYCLES | SAFE ROUTES TO SCHOOL- INFRASTRUCTURE |  | SRSI | Jessica Griffin | 250000 | 250000 | 0 | 0 | 0 |  | Other | Will be obligated by Aug. 2013 | SIDEWALKS, CROSSWALKS, LIGHTING, ADA IMPROVEMENTS, TRAIN IMPROVEMENTS AND CURB EXTENSTIONS
W100040 | 2012 | 1 | MESILLA |  | 0 | 0 | 0 | VARIOUS LOCAL STREETS AROUND MESILLA VALLEY SCHOOLS | OTHER | SAFE ROUTES TO SCHOOL- INFRASTRUCTURE |  | SRSI | Jessica Hunter | 250000 | 250000 | 0 | 0 | 250000 | 2012-09-18 | Local Let
W100080 | 2013 | 1 | LAS CRUCES |  | 0 | 0 | 0 | LAS CRUCES PUBLIC SCHOOLS | FACILITIES FOR PEDESTRIANS & BICYCLES | SAFE ROUTES TO SCHOOL- INFRASTRUCTURE |  | SRSI | Jessica Hunter | 500000 | 500000 | 0 | 0 | 0 |  | Other
W200061 | 2012 | 2 | HOBBS |  | 0 | 0 | 0 | CITY OF HOBBS PHASE 2 | OTHER | SAFE ROUTES TO SCHOOL- INFRASTRUCTURE |  | SRSI | Jessica Griffin | 250000 | 250000 | 0 | 0 | 250000 | 2012-09-19 | Local Let |  | INFRASTRUCTURE
W200061 | 2012 | 2 | HOBBS |  | 0 | 0 | 0 | CITY OF HOBBS PHASE 2 | OTHER | SAFE ROUTES TO SCHOOL- INFRASTRUCTURE |  | SRSI | Jessica Hunter | 250000 | 250000 | 0 | 0 | 250000 | 2012-09-19 | Local Let
A300094 | 2013 | 3 | DISTRICT 3 |  | 0 | 0 | 0 | SRTS: NM 448 CORRALES RD PEDESTRIAN/CROSSWALK IMPROVEMENTS - FROM CABEZON RD (APPROX. MP 7) TO APPROX. MILEPOINT 9 | OTHER | SAFE ROUTES TO SCHOOL- INFRASTRUCTURE |  | SRSI | NMDOT UNASSIGNED PDE | 50000 | 50000 | 0 | 0 | 0 |  | DOT Let
W500012 | 2013 | 5 | FARMINGTON | FL5377 | 0 | 0 | 0 | FROM NORTHSIDE OF APACHE ST. | FACILITIES FOR PEDESTRIANS & BICYCLES | SAFE ROUTES TO SCHOOL- INFRASTRUCTURE | MONIES IN THE AMOUNT OF $185,000.00 MOVED FROM CN W500013 AT THE REQUEST OF THE FARMINGTON MPO | SRSI | Jessica Griffin | 250000 | 250000 | 0 | 0 | 0 |  | Local Let | Will be obligated by Aug. 2013 | SIDEWALK IMPROVEMENTS AND PEDESTRIAN RAILINGS; CROSSWALK AND OTHER PEDESTRIAN IMPROVEMENTS
SRSI Total | [13 empty] | 2115000 | 2115000 | 0 | 0 | 1000000
W900040 | 2012 | 0 | NMDOT - Safe Routes to Schools Program |  | 0 | 0 | 0 | SAFE ROUTES TO SCHOOL | ADMINISTRATION | SAFE ROUTES TO SCHOOL-PROGRAMS |  | SRSP | Jessica Griffin | 60000 | 60000 | 0 | 0 | 60000 | 2012-09-14 | Other |  | ADMINISTRATIVE PROGRAM COSTS
W900050 | 2012 | 0 | NMDOT - Safe Routes to Schools Program |  | 0 | 0 | 0 | SRTS, UNM PROGRAM | SAFETY AND EDUCATION FOR PEDESTRIANS/BIC | SAFE ROUTES TO SCHOOL-PROGRAMS |  | SRSP | Jessica Griffin | 130063 | 130063 | 0 | 0 | 130062 | 2012-09-14 | Other |  | ASSISTANCE, MARKETING, EDUCATING COMMUNITIES & ENCOURAGEMENT
W100032 | 2013 | 1 | NMDOT - Safe Routes to Schools Program |  | 0 | 0 | 0 | SRTS PROGRAM | ADMINISTRATION | SAFE ROUTES TO SCHOOL-PROGRAMS |  | SRSP | Jessica Griffin | 64281 | 64281 | 0 | 0 | 0 |  | Other |  | ASSISTANCE, MARKETING, EDUCATING COMMUNITIES & ENCOURAGEMENT
SRSP Total | [13 empty] | 254344 | 254344 | 0 | 0 | 190062
[9 empty] | SAFETY TOTAL |  |  |  |  | 46347290 | 43030266 | 3267880 | 49144 | 24743282.88
Need to be obligated, they are in FY 12